## Feature Tracker
Module Name | Feature / Requirement | SRS Scenario / Specific Clause | Development Status | QA Status | Functional Testing | UAT | Production
01. Onboarding & Authentication | Language Selection | Users choose English or Arabic on first launch; Arabic mirrors layout to Right-to-Left. Preference stored locally on device. | Done | Pending | Pending | Pending | Pending
| Product Introduction Carousel | Swipeable 3-card slider highlighting scheduling, inventory, and snag verification for first-time users. | Pending | Pending | Pending | Pending | Pending
| Session Persistence | Returning users bypass login if a valid session is saved on-device; routes directly to project dashboard or SuperAdmin console. | Done | Pending | Pending | Pending | Pending
| Unified Credentials Verification | Single login screen for org members and SuperAdmins; system routes based on email domain/type after password check. | Done | Pending | Pending | Pending | Pending
| Password Recovery Flow | Self-service reset via 6-digit OTP (min 6 chars new password); generic confirmation message prevents email enumeration. | Done | Pending | Pending | Pending | Pending
| Token Lifecycle | Active sessions expire after 1 hour inactivity with background refresh; persistent login lasts up to 7 days. | Done | Pending | Pending | Pending | Pending
| Self-Service Company Registration | New organizations register with name, company email, phone, and password to initiate workspace setup. | Done | Pending | Pending | Pending | Pending
| OTP Verification & Auto Workspace Setup | 6-digit email OTP confirms registration; auto-creates workspace, default Admin role, and 14-day Silver Trial. | Done | Pending | Pending | Pending | Pending
| Platform Telemetry Overview | SuperAdmin dashboard shows total/active/trialing/suspended organization counts in real time. | Done | Pending | Pending | Pending | Pending
| Tenant Management & Search | Searchable directory of all registered organizations, filterable by status (All/Active/Trial/Suspended). | Done | Pending | Pending | Pending | Pending
| Manual Subscription Provisioning | SuperAdmin can change plan tier, toggle account status, adjust trial end date, or override user/project limits. | Done | Pending | Pending | Pending | Pending
| Plan Upgrade Request Queue | SuperAdmin reviews pending plan-upgrade requests; approval auto-applies new plan limits, rejection archives with a note. | Done | Pending | Pending | Pending | Pending
02. RBAC & User Management | Directory Browsing & Search | Central roster of all team members; searchable by name/email, shows role, projects, and account status. | Done | Pending | Pending | Pending | Pending
| Account Status Management | Admin can Suspend or Deactivate an employee profile, instantly logging them out and blocking access. | Done | Pending | Pending | Pending | Pending
| Customized Role Creation | Admin creates roles (e.g., Senior Surveyor) with title, description, and a configurable permission matrix. | Done | Pending | Pending | Pending | Pending
| Fine-Grained Permission Matrix | Per-module toggles for View/Create/Edit/Delete/Approve/Complete/Assign; View is a prerequisite for all other actions. | Done | Pending | Pending | Pending | Pending
| System-Role Protection Locks | Default Admin role is locked — cannot be edited, renamed, or deleted, preventing accidental lockout. | Done | Pending | Pending | Pending | Pending
| Invitation & Duplicate Validation | Invite form validates unique email and phone across the platform before allowing submission. | Done | Pending | Pending | Pending | Pending
| Temporary Credentials & Welcome Dispatch | System auto-generates a temp password and emails login credentials, role, and assigned projects to new hires. | Done | Pending | Pending | Pending | Pending
| First-Time Profile Activation | New employees are forced to set a new password on their first login before dashboard access is granted. | Done | Pending | Pending | Pending | Pending
| Project-Level Access Controls | Non-admin staff only see projects they're explicitly assigned to; Admin role has wildcard access to all projects. | Done | Pending | Pending | Pending | Pending
03. Templates & Preconfiguration | Category Management | Admin organizes the template library into categories (e.g., Luxury Residential) with unique names per org. | Done | Pending | Pending | Pending | Pending
| Blueprint Configuration Wizard | Defines a reusable template: name, category, target built-up area, estimated duration, and budget band. | Done | Pending | Pending | Pending | Pending
| Template Status Lifecycle | Templates move through Draft → Active → Archive; only Active templates are selectable for new projects. | Done | Pending | Pending | Pending | Pending
| Pre-Populated Item Groups (Baseline BOQ) | Reusable item groups (e.g., Earthworks) with name, unit, typical quantity, and baseline rate; subtotal auto-calculated. | Done | Pending | Pending | Pending | Pending
| Template Cloning Mechanics | Selecting a template auto-populates project category, area, budget, target end date, and clones BOQ + reference docs. | Done | Pending | Pending | Pending | Pending
04. Project Initialization | Project Creation Wizard | Intake form for Construction or Interior project type: name, priority, category, currency, client contact, survey toggle. | Done | Pending | Pending | Pending | Pending
| Project Status Lifecycle | Tracks project phase from Initialized through Ongoing, Under Snagging, Pending Handover, to Handover Completed. | Done | Pending | Pending | Pending | Pending
| Site Location Pinning | Manager searches or pins the site on a map, or auto-captures GPS coordinates while standing on-site. | Done | Pending | Pending | Pending | Pending
| Attendance Geofence Radius | Configurable check-in boundary (default 100m) that field workers must be inside to submit attendance. | Done | Pending | Pending | Pending | Pending
| Workspace Documents & Reference Files | Repository for blueprints/contracts with file metadata and a Document Review Status (Pending/Approved/Rejected). | Done | Pending | Pending | Pending | Pending
| Budget Audit Ledger | Starting budget creates the first Budget History entry, tagged 'Estimated Budget' and auto-Approved. | Done | Pending | Pending | Pending | Pending
05. Site & Space Surveys | Civil Site Surveys (Construction) | Surveyor logs accessibility, power/water supply, terrain notes, and photo evidence for construction sites. | Done | Pending | Pending | Pending | Pending
| Spatial Dimension Surveys (Interior) | Surveyor logs room count, ceiling heights, lighting, ventilation, and styling notes for interior fitouts. | Done | Pending | Pending | Pending | Pending
| Survey Review & Approval Loop | Admin approves or rejects submitted surveys; approval unlocks project status transition to Planning. | Done | Pending | Pending | Pending | Pending
| Budget Revision Request Trigger | Surveyor can flag a budget-affecting finding with recommended amount and justification, routed to a chosen approver. | Done | Pending | Pending | Pending | Pending
06. Technical Drawings & Annotations | Plan Folders & Blueprint Directory | Drawings organized into category folders (Architectural, Structural, MEP, Landscape) per project. | Done | Pending | Pending | Pending | Pending
| Multi-Version Document Registry | New uploads auto-increment version number; drafts default to Draft status; older versions are archived. | Done | Pending | Pending | Pending | Pending
| Sequential Review & Multi-Approver Workflows | Plan status stays Pending until all assigned approvers respond; any single rejection sets status to Rejected. | Done | Pending | Pending | Pending | Pending
| Coordinate-Pinned Feedback (Annotations) | Relative (0.0-1.0) coordinate pins on drawings support comments and photo/video attachments. | Done | Pending | Pending | Pending | Pending
07. BOQ Management | BOQ Entry & Spreadsheet Import Wizard | Manual line-item entry or Excel/CSV import with column mapping (Description, Quantity, Unit Cost, Room). | Done | Pending | Pending | Pending | Pending
| Room & Space Assignment | BOQ items can link to a specific room for interior fitout tracking and reporting. | Done | Pending | Pending | Pending | Pending
| Bulk Status & Approval Routing | Multiple draft items can be submitted for approval, or multiple pending items bulk approved/rejected, at once. | Done | Pending | Pending | Pending | Pending
| Historical Scope Versioning | Approved items requiring revision spawn a new Version 2 draft; original remains active until the revision is approved. | Done | Pending | Pending | Pending | Pending
| BOQ Item Data Structure & Cost Calculation | Tracks group, item number, description, unit, quantity, unit cost, and auto-calculated total cost. | Done | Pending | Pending | Pending | Pending
08. Budget Management | Dynamic Budget History Ledger | Array of budget iterations; active budget is the amount of the latest entry with status Approved. | Done | Pending | Pending | Pending | Pending
| Budget Revision Requests (from Survey) | Site survey findings that affect budget create a Pending ledger entry and notify the selected approver. | Done | Pending | Pending | Pending | Pending
| BOQ Change Order Integration | Approving a v2+ BOQ revision auto-calculates the cost delta and appends a new approved budget ledger entry. | Done | Pending | Pending | Pending | Pending
09. Schedule, Milestones & Tasks | Primavera P6 XER Parser | Imports .XER files, mapping PROJWBS nodes to Milestones and TASK rows to sub-tasks with start/end dates. | Done | Pending | Pending | Pending | Pending
| Interactive Schedule Board | Manual milestone/task creation with due dates, assignees, and a Gantt-style board view. | Done | Pending | Pending | Pending | Pending
| Task Assignment & Dispatch Engine | Tasks are assigned to specific team members, triggering dashboard alerts and emails. | Done | Pending | Pending | Pending | Pending
| Field Completion & Verification | Marking a task complete requires a comment and photo attachment; completed tasks are locked from editing. | Done | Pending | Pending | Pending | Pending
10. Daily Work Progress Logs (DPR) | Daily Log Intake Form | Captures milestone link, accomplishment description (max 200 chars), progress %, and photo evidence. | Done | Pending | Pending | Pending | Pending
| Chronological Progress Feed & Media Gallery | Groups daily reports and photos into a calendar timeline and date-grouped photo grid. | Done | Pending | Pending | Pending | Pending
| Daily Progress Capacity Analytics | Computes today's logged %, remaining capacity, weekly trend bars, and per-milestone activity breakdown. | Done | Pending | Pending | Pending | Pending
11. Material & Inventory | Material Catalog & Stock Ledger | Tracks item name, unit, interior finish details, and total received vs. consumed with a virtual balance. | Done | Pending | Pending | Pending | Pending
| Material Requests (Field-to-Office) | Site engineers submit item/quantity/comment requests when on-site stock runs low. | Done | Pending | Pending | Pending | Pending
| Receipt Verification (GRN) | Storekeeper logs vendor, challan number, invoice number, and photo proof; auto-increments totalReceived. | Done | Pending | Pending | Pending | Pending
| Usage & Consumption Logs | Consumption entries linked to a task; negative-stock guard blocks any entry exceeding the available balance. | Done | Pending | Pending | Pending | Pending
12. Transaction Ledger & Expenses | Double-Entry Transaction Ledger | Records Incoming/Outgoing/Debit Note/Purchase Payment entries with amount, party, method, and reference number. | Done | Pending | Pending | Pending | Pending
| Expense Classification & Receipts | Categorizes transactions (RA Bill, Material Advance, Petty Cash) with UTR/cheque references and invoice uploads. | Done | Pending | Pending | Pending | Pending
| Financial Margin & Overage Monitoring | Flags a Budget Overage alert when total outflows exceed the latest approved project budget. | Done | Pending | Pending | Pending | Pending
13. Risk Management | Risk Profiling & Classification | Captures title, category (Logistics/Safety/Financial/etc.), impact, probability, and an assigned Risk Owner. | Done | Pending | Pending | Pending | Pending
| Mitigation Progress Ledger | Logs update notes and progress %; reaching 100% auto-transitions risk status to Resolved. | Done | Pending | Pending | Pending | Pending
| Escalation Matrix Manager | Configures response-time-windowed escalation tiers (L1/L2/L3) mapped to specific roles and users. | Done | Pending | Pending | Pending | Pending
14. Snags & Quality Issues | Defect Intake & Image Capture | Captures title, description, priority (Low-Critical), room link, category, and an initial defect photo. | Done | Pending | Pending | Pending | Pending
| Spatial Room Mapping | Snags link to a specific room and category (Flooring, Walls, Ceiling, Electrical, etc.). | Done | Pending | Pending | Pending | Pending
| Contractor Assignment & Dispatch | Snags route to an assigned user with an automated email notification on assignment or status change. | Done | Pending | Pending | Pending | Pending
| Verification & Audit Loop | Status flows Draft to Open to In Progress to Resolved to Closed; only the reporter/Admin can Close. | Done | Pending | Pending | Pending | Pending
15. Handover Verification | Automated Readiness Validation Checklist | Scans drawings, BOQ, milestones, risks, and snags to confirm all are in a handover-ready state. | Done | Pending | Pending | Pending | Pending
| Handover Dashboard & Package Compiler | Packages approved drawings, BOQ items, and milestone certificates into a single client-facing package. | Done | Pending | Pending | Pending | Pending
| Approval Sign-off Routing | Manages status transitions Ongoing to Pending Handover to Completed/Rejected, capturing rejection reasons. | Done | Pending | Pending | Pending | Pending
16. Post-Handover Support | Fitout Registry & FFE Specification | Registers FFE items (brand, model, finish, room) with status Planned to Ordered to Delivered to Installed. | Done | Pending | Pending | Pending | Pending
| Warranty Claim Intake & Work Orders | Clients log post-handover claims with photos; PM creates and assigns a maintenance work order. | Done | Pending | Pending | Pending | Pending
| Warranty Cost Ledger & Archival Manager | Groups Warranty Expense transactions for margin auditing; locks project data once archived. | Done | Pending | Pending | Pending | Pending
17. Vendor & Procurement Mgmt (NEW) | Vendor Directory & Purchase Order Generation (Web) | Vendor Directory CRUD (name, contact, GST/tax ID, rate contracts); auto-generate PO from an approved Material Request with vendor selection, real-time budget-overage warning vs. linked BOQ item, PDF generation and email dispatch. [2-Week Plan: Day 1-4] | Not Started | Pending | Pending | Pending | Pending
| PO Status View & GRN Linking (App) | Mobile view of PO status/details; log GRN linked to a specific PO with a quantity-mismatch flag if received differs from ordered. [2-Week Plan: Day 1-4] | Not Started | Pending | Pending | Pending | Pending
02. RBAC & Approvals (Extension) | Multi-Level Approval Hierarchy Engine (Web) | Org Settings screen to configure approval chains per module (Budget, BOQ, Payment Request, Material Request); named approvers per level, remarks-required rules. [2-Week Plan: Day 1-3] | Not Started | Pending | Pending | Pending | Pending
| Approval Action & Push Notifications (App) | Approve / Reject / Partial-Approve action screen with mandatory remark; push notification on reaching a user's level; chain status view. [2-Week Plan: Day 1-3] | Not Started | Pending | Pending | Pending | Pending
08/12. Budget & Ledger (Extension) | Payment Request Object & Review Screen (Web) | New Payment Request object between Budget/BOQ and Transaction Ledger; approval routed via the Approval Hierarchy Engine; review screen shows linked GRN, progress, and open snags before sign-off. [2-Week Plan: Day 3-5] | Not Started | Pending | Pending | Pending | Pending
| Payment Request Mobile Flow (App) | Mobile flow for Finance/PM to raise a payment request on the go; approvers review and approve/reject with the same contextual evidence on a phone screen. [2-Week Plan: Day 3-5] | Not Started | Pending | Pending | Pending | Pending
07/10. BOQ & Progress (Extension) | Installed-Progress-to-Value Rollup (Web) | BOQ Material/Value Rollup dashboard: budgeted vs. installed quantity/value per BOQ line item, updated in real time. [2-Week Plan: Day 4-7] | Not Started | Pending | Pending | Pending | Pending
| Progress Update UX (App) | Quick tap-to-update UX on-site to log % complete against a BOQ item. [2-Week Plan: Day 4-7] | Not Started | Pending | Pending | Pending | Pending
10. Daily Progress Logs (Extension) | Manpower Tracking Dashboard (Web) | Manpower summary dashboard: daily/weekly headcount by category, plotted against logged progress. [2-Week Plan: Day 5] | Not Started | Pending | Pending | Pending | Pending
| Manpower Field in DPR Entry (App) | Add a manpower count field (by category) to the existing Daily Progress Log entry form. [2-Week Plan: Day 5] | Not Started | Pending | Pending | Pending | Pending
12. Transaction Ledger (Extension) | Imprest Request Review Screen (Web) | Dedicated Imprest Request review/approval screen, separated from the general Transaction Ledger, routed through the Approval Hierarchy Engine. [2-Week Plan: Day 6] | Not Started | Pending | Pending | Pending | Pending
| Imprest Mobile Capture (App) | Mobile expense-capture form: category, amount, photo proof of receipt, submit for approval directly from site. [2-Week Plan: Day 6] | Not Started | Pending | Pending | Pending | Pending
08/12. Budget & Ledger (Extension) | Cashflow Planning View (Web) | Actuals-vs-budget cashflow view pulling from the Transaction Ledger and approved Payment Requests. [2-Week Plan: Day 7-9] | Not Started | Pending | Pending | Pending | Pending
| Cashflow Summary Dashboard (App) | Read-only summary dashboard for PM/Admin — today's position, projected vs. actual. [2-Week Plan: Day 7-9] | Not Started | Pending | Pending | Pending | Pending
18. Equipment Management (NEW) | Equipment Registry & Allocation (Web) | Equipment Registry (owned/hired) and project allocation; maintenance scheduling and billing-dispute workflow deferred to a follow-up pass. [2-Week Plan: Day 8-10] | Not Started | Pending | Pending | Pending | Pending
| Daily Equipment Usage Logging (App) | Daily equipment usage logging: start/end time, fuel filled, operator, GPS location (reusing existing geofencing). [2-Week Plan: Day 8-10] | Not Started | Pending | Pending | Pending | Pending

## Legend & Notes
Sky-Lite Feature Tracker — Legend & Notes
Color Legend — Development Status
Done | Feature is specified/built per module documentation.
Partially Done | Feature is partially implemented — see notes in SRS column.
Not Started | Feature is pending development — includes all 2-Week Plan items.
Color Legend — QA / Functional Testing / UAT / Production
Pending | Default status for every row in this snapshot — update as each stage is actually completed.
Assumptions & Notes
- Column 'Functional Testing' replaces the 'Unifoods Functional' label from the reference screenshot — that name appeared to be carried over from a different project's template. Rename back if intentional.
- 'Development Status = Done' for Modules 01-16 reflects that these are fully specified in the Sky-Lite module documentation (v2 lite). It does not confirm actual code-complete/tested status in your repo — update per-row if any feature is still in progress.
- All downstream stages (QA, Functional Testing, UAT, Production) default to 'Pending' for every row, matching the pattern in the reference screenshot. Update these as work moves through each stage.
- Rows tagged '(NEW)' or '(Extension)' in the Module Name column, plus every row referencing '[2-Week Plan: Day X-Y]' in the SRS column, are the 8 features from the 2-Week Critical Feature Build Plan (Web + App), split into separate Web and App rows for tracking accuracy.
- Module Name cells are merged per contiguous block for readability — do not insert new rows inside a merged block without first unmerging.

## Pending Roadmap
Module Name | Feature / Requirement | SRS Scenario / Specific Clause | Development Status | QA Status | Functional Testing | UAT | Production | Priority / Dependencies
17. Financial Control & RA Billing (NEW) | Digital Measurement Book (MB) | Capture quantity, evidence and certified measurement | Not Started | Pending | Pending | Pending | Pending | FIN-01 ¦ Priority: Critical ¦ New. Dependencies: BOQ; DPR; drawings
| Progress-to-value engine | Convert verified progress to BOQ value | Partially Done | Pending | Pending | Pending | Pending | FIN-02 ¦ Priority: Critical ¦ Upgrade. Dependencies: FIN-01; BOQ; DPR
| RA billing | Progressive certified bills and reconciliation | Not Started | Pending | Pending | Pending | Pending | FIN-03 ¦ Priority: Critical ¦ New. Dependencies: FIN-01; FIN-02; PO
| Payment request checkpoint | Evidence-backed approval before payment | Not Started | Pending | Pending | Pending | Pending | FIN-04 ¦ Priority: Critical ¦ New. Dependencies: Ledger; receipts; FIN-01
| PO/vendor invoice reconciliation | Ordered, received, invoiced and paid matching | Not Started | Pending | Pending | Pending | Pending | FIN-05 ¦ Priority: Critical ¦ New. Dependencies: Vendor; materials; ledger
| Multi-level approval engine | Configurable L1/L2/L3 approvals, delegation and audit | Not Started | Pending | Pending | Pending | Pending | FIN-06 ¦ Priority: Critical ¦ New. Dependencies: RBAC; notifications
| Cashflow/payment-aging reporting | Projected vs actual cash and outstanding tracking | Partially Done | Pending | Pending | Pending | Pending | FIN-07 ¦ Priority: High ¦ Upgrade. Dependencies: FIN-03; FIN-04; ledger
18. Vendor & Procurement (NEW) | Vendor/subcontractor directory | Onboarding, compliance, assignment and scorecard | Not Started | Pending | Pending | Pending | Pending | VEN-01 ¦ Priority: Critical ¦ New. Dependencies: Projects; RBAC
| Purchase orders/work orders | Scope, rate, terms, budget check and approval | Partially Done | Pending | Pending | Pending | Pending | VEN-02 ¦ Priority: Critical ¦ Upgrade. Dependencies: BOQ; materials; budget
| Vendor billing/GRN reconciliation | Bill, receipt validation, dispute and payment request | Not Started | Pending | Pending | Pending | Pending | VEN-03 ¦ Priority: Critical ¦ New. Dependencies: VEN-02; FIN-04
| Vendor performance | Quality, delay, cost and resolution scorecard | Not Started | Pending | Pending | Pending | Pending | VEN-04 ¦ Priority: High ¦ New. Dependencies: Snags; schedule
19. Execution Resources (Extension) | Labour/manpower tracking | Allocation, productivity and payroll-ready totals | Partially Done | Pending | Pending | Pending | Pending | EXE-01 ¦ Priority: High ¦ Upgrade. Dependencies: Attendance; DPR; schedule
| Equipment management (Module 17) | Owned/hired equipment, hours, fuel, maintenance and downtime | Not Started | Pending | Pending | Pending | Pending | EXE-02 ¦ Priority: High ¦ New. Dependencies: Ledger; risk; geofencing
| Advanced Gantt/resource planning | Dependencies, critical path, baseline and resource conflicts | Partially Done | Pending | Pending | Pending | Pending | EXE-03 ¦ Priority: High ¦ Upgrade. Dependencies: Schedule; EXE-01; EXE-02
| Pre-execution readiness checklist | Design, permit, vendor, resource, safety and site gates | Not Started | Pending | Pending | Pending | Pending | EXE-04 ¦ Priority: Medium ¦ New. Dependencies: Project; survey; BOQ
20. Workflow & Collaboration (NEW) | Unified cross-project inbox | One queue for tasks, approvals, comments and reminders | Not Started | Pending | Pending | Pending | Pending | COL-01 ¦ Priority: Critical ¦ New. Dependencies: Notifications; FIN-06
| Role-based notification rules | Channel, priority, digest, escalation and preferences | Partially Done | Pending | Pending | Pending | Pending | COL-02 ¦ Priority: High ¦ Upgrade. Dependencies: COL-01
| Cross-module comments/tasks | Reusable collaboration on financial/operational records | Not Started | Pending | Pending | Pending | Pending | COL-03 ¦ Priority: High ¦ New. Dependencies: COL-01
| No-code workflow/custom fields | Admin-configured fields, terms and approval workflows | Not Started | Pending | Pending | Pending | Pending | COL-04 ¦ Priority: High ¦ New. Dependencies: FIN-06; RBAC
| External organization collaboration | Scoped external sharing without losing tenant isolation | Not Started | Pending | Pending | Pending | Pending | COL-05 ¦ Priority: Medium ¦ Product decision. Dependencies: RBAC; projects
21. Platform Operations (Extension) | Unified management dashboard | Cross-project commercial and operational alerts | Partially Done | Pending | Pending | Pending | Pending | OPS-01 ¦ Priority: High ¦ Upgrade. Dependencies: COL-01; FIN-07
| Financial audit controls | Immutable evidence and segregation-of-duty controls | Partially Done | Pending | Pending | Pending | Pending | OPS-02 ¦ Priority: High ¦ Upgrade. Dependencies: FIN-04; FIN-06
22. Design & Interior Selections (NEW) | Mood boards/finish selection | Room-wise visual options and client sign-off | Not Started | Pending | Pending | Pending | Pending | DES-01 ¦ Priority: Medium ¦ New. Dependencies: Rooms; documents; approvals
| Client-facing design approval | Extend technical review to visual design packages | Partially Done | Pending | Pending | Pending | Pending | DES-02 ¦ Priority: High ¦ Partial. Dependencies: Drawings; DES-01
| Design-to-BOQ linkage | Link approved design choices to quantities, rates and revisions | Not Started | Pending | Pending | Pending | Pending | DES-03 ¦ Priority: High ¦ New. Dependencies: DES-01; BOQ
| Assisted BOQ/value engineering | Draft BOQ and approved alternatives with human review | Not Started | Pending | Pending | Pending | Pending | DES-04 ¦ Priority: Medium ¦ New. Dependencies: DES-03; budget
| Furniture/OEM production stages | Cutting, assembly, finish, QC and dispatch | Partially Done | Pending | Pending | Pending | Pending | INT-01 ¦ Priority: High ¦ Upgrade. Dependencies: FFE; VEN-02
| Room readiness dashboard | Completion from value, FFE, snags and tasks | Not Started | Pending | Pending | Pending | Pending | INT-02 ¦ Priority: High ¦ New. Dependencies: FIN-02; snags; FFE
| Room-wise/phased handover | Partial handover certificates and readiness | Partially Done | Pending | Pending | Pending | Pending | INT-03 ¦ Priority: High ¦ Upgrade. Dependencies: Handover; INT-02
| As-built measurement verification | Gate custom orders on verified dimensions | Not Started | Pending | Pending | Pending | Pending | INT-04 ¦ Priority: Medium ¦ New. Dependencies: Survey; VEN-02
23. Handover, Certification & AMC (Extension) | Test certificate/compliance register | Templates, expiry, review and asset/BOQ links | Not Started | Pending | Pending | Pending | Pending | HND-01 ¦ Priority: Medium ¦ New. Dependencies: Documents; BOQ; handover
| Asset-linked documentation | Tag manuals/certificates/warranties to assets | Partially Done | Pending | Pending | Pending | Pending | HND-02 ¦ Priority: Medium ¦ Upgrade. Dependencies: FFE; HND-01
| Warranty expiry/lifecycle alerts | Expiry reminders, vendor/SLA links and asset history | Partially Done | Pending | Pending | Pending | Pending | HND-03 ¦ Priority: Medium ¦ Partial. Dependencies: Warranty; notifications
| AMC/service-ticket system | Contracts, visits, SLA, technician work and closure | Partially Done | Pending | Pending | Pending | Pending | HND-04 ¦ Priority: Medium ¦ Upgrade. Dependencies: Warranty; ledger
| Structured handover package | System/room/asset checklist and acceptance package | Partially Done | Pending | Pending | Pending | Pending | HND-05 ¦ Priority: High ¦ Upgrade. Dependencies: HND-01 to HND-04
24. Intelligence & Reporting (Extension) | Cost vs actual variance | BOQ/budget/PO/actual/billed/payment comparison | Partially Done | Pending | Pending | Pending | Pending | INTEL-01 ¦ Priority: High ¦ Upgrade. Dependencies: FIN-02 to FIN-07
| Delay prediction/early warnings | Explainable alerts from schedule, DPR, risk and resources | Not Started | Pending | Pending | Pending | Pending | INTEL-02 ¦ Priority: Medium ¦ New. Dependencies: EXE-01 to EXE-03
| Project profitability | Forecast and actual margin including warranty/resources | Partially Done | Pending | Pending | Pending | Pending | INTEL-03 ¦ Priority: High ¦ Upgrade. Dependencies: FIN-07; EXE-01/02
| Auto-distributed DPR/reports | Verified report and subscriber distribution | Partially Done | Pending | Pending | Pending | Pending | INTEL-04 ¦ Priority: Medium ¦ Upgrade. Dependencies: DPR; COL-02

## Pending Roadmap Notes
Pending Roadmap — Legend & Notes
Development Status | Not Started = a net-new feature or a product decision; Partially Done = existing documented module base requires a substantial upgrade.
QA / Functional Testing / UAT / Production | All are set to Pending because these roadmap features have not been verified through their delivery lifecycle.
Priority | Critical features form the commercial control chain: measurement → value → RA bill → approval → payment → reconciliation.
Important | Modules 01–16 remain in the original Feature Tracker. The Pending Roadmap sheet avoids incorrectly classifying their documented foundations as completely missing.
Recommended first release | Unified Inbox + Multi-level Approval Engine, followed by Vendor/PO/Payment Request, then Measurement-to-RA-Billing.